## Risks
ID | Risk | Asset | Likelihood (1-5) | Impact (1-5) | Score | Controls in place | Residual | Treatment | Owner | Status
R-01 | Sensitive data stored under a lower classification (found: internal/notes-export.csv) | Data bucket | 4 | 4 |  | Macie, tags, prefixes, remediation script | Medium | Reduce: recurring discovery | Ahmed Ali | Open
R-02 | A bucket made public by mistake | S3 | 2 | 5 |  | Account + bucket BPA, Access Analyzer, GuardDuty alert | Low | Reduce | Ahmed Shaaban | Open
R-03 | Credentials or secrets pushed to GitHub | Repository | 3 | 5 |  | CloudShell only, .gitignore, push protection, PR review, generated secrets | Low | Reduce | Ahmed Ali | Open
R-04 | A KMS key disabled or deleted, data unreadable | KMS keys | 2 | 5 |  | Admin/user split, alert on DisableKey/ScheduleKeyDeletion, 7-30 day wait | Low | Reduce | Ammar | Open
R-05 | All lab members have AdministratorAccess | AWS account | 3 | 4 |  | MFA, CloudTrail, 4-hour sessions, budget alert, teardown | Medium | Accept for the lab only | Ahmed Ali | Accepted
R-06 | API abuse or credential stuffing | API Gateway | 3 | 3 |  | Cognito, throttling, WAF rate rule | Low | Reduce | Mohamed Essam | Open
R-07 | Personal data exposed through API responses or logs | Lambda / CloudWatch | 3 | 4 |  | Minimal responses, safe log lines, unit tests | Low | Reduce | Mohamed Essam | Open
R-08 | Unexpected cloud cost | Account | 3 | 2 |  | Budget alerts, paid features off by default, teardown script | Low | Reduce | Ahmed Ali | Open
R-09 | Old object versions keep deleted sensitive data | Data bucket | 3 | 3 |  | Noncurrent version expiry (30 days), remediation deletes versions | Low | Reduce | Ahmed Shaaban | Open

## Scale
Score = likelihood x impact
15-25 high, 8-14 medium, 1-7 low
Residual = what is left after the controls in place